## Sheet1
Project Risk | Risk Type | Probability | Impact on Project | Cost to Project (Quantitative) | Cost to Project (Qualitative) | Mitigation Plan | Owner
Specific questions weren't tailored enough to each individual | Strategic Risk | Low | Medium | Grade reduction | Individuals do not benefit from panel interview experience | Avoid: Encourage each member to share their specific career goals during in-class activities. [Insert specific protocol; e.g., On group work day 1, Chelsea will make sure that each team member has shared a job description] | Chelsea
Interview "choreography" is awkward, don't know who asks questions when | Strategic Risk | High | Medium | Grade reduction; timing of the panel interview experience is compromised causing individuals to be rushed | Rapport and confidence is sacrificed in the interview experience | Avoid: Delegate a "leader" or "hiring manager" who acts as a question lead for each interview. [Insert specific protocol; e.g., Abobo is the team lead for Chelsea's interview] | Abobo
Team members do not come to class | Performance Risk | High | High | Grade reduction: team activities are not completed | Rapport is not built in the team; cannot tailor assignments to individuals' goals | Reduce: Create protocol for missing a group assignment in first meeting. [Insert specific protocol; e.g., April schedules a Zoom meeting for theThursday morning following class to make-up] | April
Class is canceled one day | External Risk | High | Low | None | Time spent at home to complete assignment; lack of in-person collaboration | Accept